## Timeline
Major Range Change Schedule |  |  |  |  | as of 3.8.17
[6 empty] | supply this list of discos to DP (will NOT stop ordering) this gives 1st look to help manage inventory | [10 empty] | Keep markdowns @ 50%
Initial Range & Base POG Approved
[5 empty] | New Items | Disco Items | Buyer | VP/Director | Final Range Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call
[5 empty] | 0 | 0 | 0 | 7 | 5 | 1 | 7 | 20 | 7 | 2 | 1 | 7 | 10 | 0 | 17
| Groc, D/FF, Taxable Groc - Wks Before Landing |  |  |  | 12 | 12 | 12 | 12 | 11 | 10.2857 | 10.1429 | 9.1429 | 6.2857 | 5.2857 | 5 | 4.8571 | 3.8571 | 2.4286 | 2.4286
[5 empty] | 0 | 0 | 0 | 7 | 9 | 1 | 7 | 20 | 5 | 2 | 1 | 7 | 38 | 0 | 17
| GMD/HBC - Wks Before Landing |  |  |  | 16.2857 | 16.2857 | 16.2857 | 16.2857 | 15.2857 | 14 | 13.8571 | 12.8571 | 10 | 9.2857 | 9 | 8.8571 | 7.8571 | 2.4286 | 2.4286
| Cycle 3 | 2017-01-30
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Cheese | Dairy |  |  | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-14 | 2016-11-19 | 2016-11-20 | 2016-11-27 | 2016-12-17 | 2016-12-24 | 2016-12-26 | 2016-12-27 | 2017-01-03 | 2017-01-13 | 2017-01-13 | 2017-01-30 | 2017-01-30 | 0
Tracking
2 | Personal Cleansing/Bath | GMD-HBC |  |  | 2016-10-08 | 2016-10-08 | 2016-10-08 | 2016-10-08 | 2016-10-15 | 2016-10-24 | 2016-10-25 | 2016-11-01 | 2016-11-21 | 2016-11-26 | 2016-11-28 | 2016-11-29 | 2016-12-06 | 2017-01-13 | 2017-01-13 | 2017-01-30 | 2017-01-30 | 0
Tracking
3 | Facial Tissue | GMD-HBC |  |  | 2016-10-08 | 2016-10-08 | 2016-10-08 | 2016-10-08 | 2016-10-15 | 2016-10-24 | 2016-10-25 | 2016-11-01 | 2016-11-21 | 2016-11-26 | 2016-11-28 | 2016-11-29 | 2016-12-06 | 2017-01-13 | 2017-01-13 | 2017-01-30 | 2017-01-30 | 0
Tracking
4 | Frozen Potatoes | Frozen |  |  | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-14 | 2016-11-19 | 2016-11-20 | 2016-11-27 | 2016-12-17 | 2016-12-24 | 2016-12-26 | 2016-12-27 | 2017-01-03 | 2017-01-13 | 2017-01-13 | 2017-01-30 | 2017-01-30 | 0
Tracking
5 | Frozen Dinners/Entrees | Frozen |  |  | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-14 | 2016-11-19 | 2016-11-20 | 2016-11-27 | 2016-12-17 | 2016-12-24 | 2016-12-26 | 2016-12-27 | 2017-01-03 | 2017-01-13 | 2017-01-13 | 2017-01-30 | 2017-01-30 | 0
Tracking
6 | Cosmetics | GMD-HBC |  |  | 2016-10-08 | 2016-10-08 | 2016-10-08 | 2016-10-08 | 2016-10-15 | 2016-10-24 | 2016-10-25 | 2016-11-01 | 2016-11-21 | 2016-11-26 | 2016-11-28 | 2016-11-29 | 2016-12-06 | 2017-01-13 | 2017-01-13 | 2017-01-30 | 2017-01-30 | 0
Tracking
| Cycle 4 | 2017-02-13
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Pasta Sauce | Grocery |  |  | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-28 | 2016-12-03 | 2016-12-04 | 2016-12-11 | 2016-12-31 | 2017-01-07 | 2017-01-09 | 2017-01-10 | 2017-01-17 | 2017-01-27 | 2017-01-27 | 2017-02-13 | 2017-02-13 | 0
Tracking
2 | Popcorn | Grocery |  |  | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-28 | 2016-12-03 | 2016-12-04 | 2016-12-11 | 2016-12-31 | 2017-01-07 | 2017-01-09 | 2017-01-10 | 2017-01-17 | 2017-01-27 | 2017-01-27 | 2017-02-13 | 2017-02-13 | 0
Tracking
3 | Snack Nuts | Grocery |  |  | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-28 | 2016-12-03 | 2016-12-04 | 2016-12-11 | 2016-12-31 | 2017-01-07 | 2017-01-09 | 2017-01-10 | 2017-01-17 | 2017-01-27 | 2017-01-27 | 2017-02-13 | 2017-02-13 | 0
| Tracking |  |  |  | 2017-01-07: Ordered Late; 2017-01-17: 2wks of Mkdn
4 | Tabletop | Tax Groc |  |  | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-28 | 2016-12-03 | 2016-12-04 | 2016-12-11 | 2016-12-31 | 2017-01-07 | 2017-01-09 | 2017-01-10 | 2017-01-17 | 2017-01-27 | 2017-01-27 | 2017-02-13 | 2017-02-13 | 0
Tracking
5 | Canned Dog Food | Grocery |  |  | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-28 | 2016-12-03 | 2016-12-04 | 2016-12-11 | 2016-12-31 | 2017-01-07 | 2017-01-09 | 2017-01-10 | 2017-01-17 | 2017-01-27 | 2017-01-27 | 2017-02-13 | 2017-02-13 | 0
Tracking
6 | Frozen Dinners | Grocery |  |  | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-28 | 2016-12-03 | 2016-12-04 | 2016-12-11 | 2016-12-31 | 2017-01-07 | 2017-01-09 | 2017-01-10 | 2017-01-17 | 2017-01-27 | 2017-01-27 | 2017-02-13 | 2017-02-13 | 0
Tracking
| Cycle 5 | 2017-02-27
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Milk/Creamers | Dairy |  |  | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-12 | 2016-12-17 | 2016-12-18 | 2016-12-25 | 2017-01-14 | 2017-01-21 | 2017-01-23 | 2017-01-24 | 2017-01-31 | 2017-02-10 | 2017-02-10 | 2017-02-27 | 2017-02-27 | 0
| Tracking |  |  |  | 2017-01-14: Published Late
2 | Bleach | Tax Grocery |  |  | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-12 | 2016-12-17 | 2016-12-18 | 2016-12-25 | 2017-01-14 | 2017-01-21 | 2017-01-23 | 2017-01-24 | 2017-01-31 | 2017-02-10 | 2017-02-10 | 2017-02-27 | 2017-02-27 | 0
| Tracking |  |  |  | 2017-01-14: Published Late; 2017-01-21: Late
| Cycle 6 | 2017-03-13
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Ice Cream | Frozen |  |  | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-26 | 2016-12-31 | 2017-01-01 | 2017-01-08 | 2017-01-28 | 2017-02-04 | 2017-02-06 | 2017-02-07 | 2017-02-14 | 2017-02-24 | 2017-02-24 | 2017-03-13 | 2017-03-13 | 0
| Tracking |  |  |  | 2017-01-28: Published Late
2 | Frozen Novelties | Frozen |  |  | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-26 | 2016-12-31 | 2017-01-01 | 2017-01-08 | 2017-01-28 | 2017-02-04 | 2017-02-06 | 2017-02-07 | 2017-02-14 | 2017-02-24 | 2017-02-24 | 2017-03-13 | 2017-03-13 | 0
| Tracking |  |  |  | 2017-01-28: Published Late
3 | Bath Tissue | Tax Grocery |  |  | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-26 | 2016-12-31 | 2017-01-01 | 2017-01-08 | 2017-01-28 | 2017-02-04 | 2017-02-06 | 2017-02-07 | 2017-02-14 | 2017-02-24 | 2017-02-24 | 2017-03-13 | 2017-03-13 | 0
Tracking
4 | Paper Towels | Tax Grocery |  |  | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-26 | 2016-12-31 | 2017-01-01 | 2017-01-08 | 2017-01-28 | 2017-02-04 | 2017-02-06 | 2017-02-07 | 2017-02-14 | 2017-02-24 | 2017-02-24 | 2017-03-13 | 2017-03-13 | 0
Tracking
| Cycle 7 | 2017-03-27
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Pancake Mix/Syrup | Grocery |  |  | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-09 | 2017-01-14 | 2017-01-15 | 2017-01-22 | 2017-02-11 | 2017-02-18 | 2017-02-20 | 2017-02-21 | 2017-02-28 | 2017-03-10 | 2017-03-10 | 2017-03-27 | 2017-03-27 | 0
Tracking
2 | Strength and Energy | GMD-HBC |  |  | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-10 | 2016-12-19 | 2016-12-20 | 2016-12-27 | 2017-01-16 | 2017-01-21 | 2017-01-23 | 2017-01-24 | 2017-01-31 | 2017-03-10 | 2017-03-10 | 2017-03-27 | 2017-03-27 | 0
Tracking
3 | Weight Management | GMD-HBC |  |  | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-10 | 2016-12-19 | 2016-12-20 | 2016-12-27 | 2017-01-16 | 2017-01-21 | 2017-01-23 | 2017-01-24 | 2017-01-31 | 2017-03-10 | 2017-03-10 | 2017-03-27 | 2017-03-27 | 0
Tracking
4 | Travel Size | GMD-HBC |  |  | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-10 | 2016-12-19 | 2016-12-20 | 2016-12-27 | 2017-01-16 | 2017-01-21 | 2017-01-23 | 2017-01-24 | 2017-01-31 | 2017-03-10 | 2017-03-10 | 2017-03-27 | 2017-03-27 | 0
Tracking
5 | CSD Soft Drinks/Chek Drinks | Grocery |  |  | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-09 | 2017-01-14 | 2017-01-15 | 2017-01-22 | 2017-02-11 | 2017-02-18 | 2017-02-20 | 2017-02-21 | 2017-02-28 | 2017-03-10 | 2017-03-10 | 2017-03-27 | 2017-03-27 | 0
Tracking
6 | Canning | GMD-HBC |  |  | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-10 | 2016-12-19 | 2016-12-20 | 2016-12-27 | 2017-01-16 | 2017-01-21 | 2017-01-23 | 2017-01-24 | 2017-01-31 | 2017-03-10 | 2017-03-10 | 2017-03-27 | 2017-03-27 | 0
| Tracking |  |  |  | 2017-01-16: Published Late
7 | Canisters & Meat Snacks | Grocery |  |  | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-09 | 2017-01-14 | 2017-01-15 | 2017-01-22 | 2017-02-11 | 2017-02-18 | 2017-02-20 | 2017-02-21 | 2017-02-28 | 2017-03-10 | 2017-03-10 | 2017-03-27 | 2017-03-27 | 0
Tracking
8 | Peanut Butter & Jelly | Grocery |  |  | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-09 | 2017-01-14 | 2017-01-15 | 2017-01-22 | 2017-02-11 | 2017-02-18 | 2017-02-20 | 2017-02-21 | 2017-02-28 | 2017-03-10 | 2017-03-10 | 2017-03-27 | 2017-03-27 | 0
Tracking
9 | Automotive | GMD-HBC |  |  | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-10 | 2016-12-19 | 2016-12-20 | 2016-12-27 | 2017-01-16 | 2017-01-21 | 2017-01-23 | 2017-01-24 | 2017-01-31 | 2017-03-10 | 2017-03-10 | 2017-03-27 | 2017-03-27 | 0
Tracking
| Cycle 8 | 2017-04-17
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Convenience Breakfast | Grocery |  |  | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-30 | 2017-02-04 | 2017-02-05 | 2017-02-12 | 2017-03-04 | 2017-03-11 | 2017-03-13 | 2017-03-14 | 2017-03-21 | 2017-03-31 | 2017-03-31 | 2017-04-17 | 2017-04-17 | 0
| Tracking |  |  |  | 2017-03-21: 2 wks Mkdn
2 | Cold Cereal | Grocery |  |  | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-30 | 2017-02-04 | 2017-02-05 | 2017-02-12 | 2017-03-04 | 2017-03-11 | 2017-03-13 | 2017-03-14 | 2017-03-21 | 2017-03-31 | 2017-03-31 | 2017-04-17 | 2017-04-17 | 0
| Tracking |  |  |  | 2017-03-21: 2 wks Mkdn
3 | Bag Cereal | Grocery |  |  | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-30 | 2017-02-04 | 2017-02-05 | 2017-02-12 | 2017-03-04 | 2017-03-11 | 2017-03-13 | 2017-03-14 | 2017-03-21 | 2017-03-31 | 2017-03-31 | 2017-04-17 | 2017-04-17 | 0
| Tracking |  |  |  | 2017-03-21: 2 wks Mkdn; 2017-03-31: 3rd Party Rack?
4 | Hot Cereal | Grocery |  |  | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-30 | 2017-02-04 | 2017-02-05 | 2017-02-12 | 2017-03-04 | 2017-03-11 | 2017-03-13 | 2017-03-14 | 2017-03-21 | 2017-03-31 | 2017-03-31 | 2017-04-17 | 2017-04-17 | 0
| Tracking |  |  |  | 2017-03-21: 2 wks Mkdn
5 | Healthy Lifestyle Bars | Grocery |  |  | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-30 | 2017-02-04 | 2017-02-05 | 2017-02-12 | 2017-03-04 | 2017-03-11 | 2017-03-13 | 2017-03-14 | 2017-03-21 | 2017-03-31 | 2017-03-31 | 2017-04-17 | 2017-04-17 | 0
Tracking
6 | CSD Soft Drinks/Chek (Wk2) | Grocery |  |  | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-30 | 2017-02-04 | 2017-02-05 | 2017-02-12 | 2017-03-04 | 2017-03-11 | 2017-03-13 | 2017-03-14 | 2017-03-21 | 2017-03-31 | 2017-03-31 | 2017-04-17 | 2017-04-17 | 0
Tracking
| Cycle 9 | 2017-05-01
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | RTD Tea | Frozen |  |  | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-13 | 2017-02-18 | 2017-02-19 | 2017-02-26 | 2017-03-18 | 2017-03-25 | 2017-03-27 | 2017-03-28 | 2017-04-04 | 2017-04-14 | 2017-04-14 | 2017-05-01 | 2017-05-01 | 0
Tracking
2 | Isotonics | Frozen |  |  | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-13 | 2017-02-18 | 2017-02-19 | 2017-02-26 | 2017-03-18 | 2017-03-25 | 2017-03-27 | 2017-03-28 | 2017-04-04 | 2017-04-14 | 2017-04-14 | 2017-05-01 | 2017-05-01 | 0
| Tracking |  |  |  | 2017-03-27: Equip?
4 | Canned Beans | Grocery |  |  | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-13 | 2017-02-18 | 2017-02-19 | 2017-02-26 | 2017-03-18 | 2017-03-25 | 2017-03-27 | 2017-03-28 | 2017-04-04 | 2017-04-14 | 2017-04-14 | 2017-05-01 | 2017-05-01 | 0
Tracking
5 | Charcoal | Tax Groc |  |  | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-13 | 2017-02-18 | 2017-02-19 | 2017-02-26 | 2017-03-18 | 2017-03-25 | 2017-03-27 | 2017-03-28 | 2017-04-04 | 2017-04-14 | 2017-04-14 | 2017-05-01 | 2017-05-01 | 0
Tracking
6 | Upscale Italian | Grocery |  |  | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-13 | 2017-02-18 | 2017-02-19 | 2017-02-26 | 2017-03-18 | 2017-03-25 | 2017-03-27 | 2017-03-28 | 2017-04-04 | 2017-04-14 | 2017-04-14 | 2017-05-01 | 2017-05-01 | 0
Tracking
| Cycle 10 | 2017-05-15
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Ketchup | Grocery |  |  | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-27 | 2017-03-04 | 2017-03-05 | 2017-03-12 | 2017-04-01 | 2017-04-08 | 2017-04-10 | 2017-04-11 | 2017-04-18 | 2017-04-28 | 2017-04-28 | 2017-05-15 | 2017-05-15 | 0
Tracking
2 | Meat Sauce | Grocery |  |  | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-27 | 2017-03-04 | 2017-03-05 | 2017-03-12 | 2017-04-01 | 2017-04-08 | 2017-04-10 | 2017-04-11 | 2017-04-18 | 2017-04-28 | 2017-04-28 | 2017-05-15 | 2017-05-15 | 0
Tracking
3 | Mustard | Grocery |  |  | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-27 | 2017-03-04 | 2017-03-05 | 2017-03-12 | 2017-04-01 | 2017-04-08 | 2017-04-10 | 2017-04-11 | 2017-04-18 | 2017-04-28 | 2017-04-28 | 2017-05-15 | 2017-05-15 | 0
Tracking
4 | Salad Dressing/Mayo | Grocery |  |  | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-27 | 2017-03-04 | 2017-03-05 | 2017-03-12 | 2017-04-01 | 2017-04-08 | 2017-04-10 | 2017-04-11 | 2017-04-18 | 2017-04-28 | 2017-04-28 | 2017-05-15 | 2017-05-15 | 0
Tracking
5 | Eye Care | GMD-HBC |  |  | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-28 | 2017-02-06 | 2017-02-07 | 2017-02-14 | 2017-03-06 | 2017-03-11 | 2017-03-13 | 2017-03-14 | 2017-03-21 | 2017-04-28 | 2017-04-28 | 2017-05-15 | 2017-05-15 | 0
| Tracking |  |  |  | 2017-02-06: PCR?
| Cycle 11 | 2017-05-30
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Coffee | Grocery |  |  | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-14 | 2017-03-19 | 2017-03-20 | 2017-03-27 | 2017-04-16 | 2017-04-23 | 2017-04-25 | 2017-04-26 | 2017-05-03 | 2017-05-13 | 2017-05-13 | 2017-05-30 | 2017-05-30 | 0
Tracking
2 | Face Care | GMD-HBC |  |  | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-12 | 2017-02-21 | 2017-02-22 | 2017-03-01 | 2017-03-21 | 2017-03-26 | 2017-03-28 | 2017-03-29 | 2017-04-05 | 2017-05-13 | 2017-05-13 | 2017-05-30 | 2017-05-30 | 0
| Tracking |  |  |  | 2017-03-21: PCR?
3 | Skin Care | GMD-HBC |  |  | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-12 | 2017-02-21 | 2017-02-22 | 2017-03-01 | 2017-03-21 | 2017-03-26 | 2017-03-28 | 2017-03-29 | 2017-04-05 | 2017-05-13 | 2017-05-13 | 2017-05-30 | 2017-05-30 | 0
Tracking
4 | Cotton Puffs | GMD-HBC |  |  | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-12 | 2017-02-21 | 2017-02-22 | 2017-03-01 | 2017-03-21 | 2017-03-26 | 2017-03-28 | 2017-03-29 | 2017-04-05 | 2017-05-13 | 2017-05-13 | 2017-05-30 | 2017-05-30 | 0
Tracking
| Cycle 12 | 2017-06-12
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Yogurt | Dairy |  |  | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-27 | 2017-04-01 | 2017-04-02 | 2017-04-09 | 2017-04-29 | 2017-05-06 | 2017-05-08 | 2017-05-09 | 2017-05-16 | 2017-05-26 | 2017-05-26 | 2017-06-12 | 2017-06-12 | 0
Tracking
2 | Candy | Grocery |  |  | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-27 | 2017-04-01 | 2017-04-02 | 2017-04-09 | 2017-04-29 | 2017-05-06 | 2017-05-08 | 2017-05-09 | 2017-05-16 | 2017-05-26 | 2017-05-26 | 2017-06-12 | 2017-06-12 | 0
Tracking
3 | Cookies/Crackers | Grocery |  |  | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-27 | 2017-04-01 | 2017-04-02 | 2017-04-09 | 2017-04-29 | 2017-05-06 | 2017-05-08 | 2017-05-09 | 2017-05-16 | 2017-05-26 | 2017-05-26 | 2017-06-12 | 2017-06-12 | 0
Tracking
| Cycle 13 | 2017-07-10
Initial Range & Base POG Approved
| Category | Dept | Category Director/VP | Status | New Items | Disco Items | Buyer | VP/Director | Lock Date | Go/No Go Call | Store Comms | Demand Planning Flag Disco Items to Stop Buying | POGs Published | New Items Initial Purchase Date | Go/No Go Call | Store Comms (All Details) | Store Markdown | New Items Due in All DCs | Final Go/No Go Call | Holiday Factor Offset (calc'ed) | Start of Cycle | Holiday Factor Off-Set for Calc
1 | Oral Care | GMD-HBC |  |  | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-25 | 2017-04-03 | 2017-04-04 | 2017-04-11 | 2017-05-01 | 2017-05-06 | 2017-05-08 | 2017-05-09 | 2017-05-16 | 2017-06-23 | 2017-06-23 | 2017-07-10 | 2017-07-10 | 0
Tracking
2 | Box Dinners | Grocery |  |  | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-24 | 2017-04-29 | 2017-04-30 | 2017-05-07 | 2017-05-27 | 2017-06-03 | 2017-06-05 | 2017-06-06 | 2017-06-13 | 2017-06-23 | 2017-06-23 | 2017-07-10 | 2017-07-10 | 0
Tracking
3 | Vinegar | Grocery |  |  | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-24 | 2017-04-29 | 2017-04-30 | 2017-05-07 | 2017-05-27 | 2017-06-03 | 2017-06-05 | 2017-06-06 | 2017-06-13 | 2017-06-23 | 2017-06-23 | 2017-07-10 | 2017-07-10 | 0
Tracking
4 | Commercial Bread | Grocery |  |  | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-24 | 2017-04-29 | 2017-04-30 | 2017-05-07 | 2017-05-27 | 2017-06-03 | 2017-06-05 | 2017-06-06 | 2017-06-13 | 2017-06-23 | 2017-06-23 | 2017-07-10 | 2017-07-10 | 0
Tracking
1 | Napkins | Tax Grocery |  |  | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-24 | 2017-04-29 | 2017-04-30 | 2017-05-07 | 2017-05-27 | 2017-06-03 | 2017-06-05 | 2017-06-06 | 2017-06-13 | 2017-06-23 | 2017-06-23 | 2017-07-10 | 2017-07-10 | 0
Tracking
Formulas:
Holiday Factor Offset (calc'ed) = [Start of Cycle]-[Holiday Factor Off-Set for Calc]

## Sheet1
| Kickoff |  |  |  |  | Project Setup (Concurrent Tasks) | [15 empty] | Pilot | [6 empty] | Rollout
| Project Proposal | Investigate Project | Present to Director | Create estimate of cost and labor impact | Present to Dept VP and Merch Ops | Project entered into SIP | Item Setup / Supply Chain Eval | Food Safety | Total Loss Eval | Workforce Mgmt | Mkting Guideline | Covering TL credit with vendor | Equipment / Supplies | POGs / MLO / Layouts | Customer Insights | QA Specs (Fresh) | SMART / Production Planning | Metrics setup | Building Training | Store Feedback / Listening Session | Go/No Go | Comms to Pilot DM/RVP | SHD Informed | Go/No Go | Comms to Pilot | Pilot Launch | Feedback | Go/No Go | Metrics Developed | Rollout Schedule | Dept VP, Merch Ops, SIP, Workforce, WOW, TL Signoff | Comms to DMs/RVPs | SHD Informed | Comms | Launch | Feedback | Actual ROI
Days for Task | [33 empty] | 16 | 0
Weeks out from MOC |  |  |  |  | 13 | 12 |  |  |  | 12 |  |  | 12 | [5 empty] | 12 | 12 | [11 empty] | 3 | 3 | 2 | 0
Due Date